## Sheet1
Test Summary Report
Test Report Date (dd-mm-yy) |  |  | 18/02/26 |  | Version: | 1
Test Information
Project Name : | PaiNamNaeWebApp |  |  |  | Project ID: | Sprint 1
Start Date(dd-mm-yy): | 18/02/26 |  |  |  | End Date: | 18/02/26
Module Name : | Register and Delete Account
Version : | v1.0 | [9 empty] | Chart Summary
Tester : | 1.นิติภูมิ ยุระรัช
2.ศุภกิจ จตุเทน
3.อัศวิน จินดาวงค์
Tester's Comments :
UAT Test Case
Test ID | Module | Test Scenario / Steps | Expected Result |  | Actual Result |  | Status
Del-01 | Register and Delete Account | Register User Account, Log in and Delete Account | Show Message "บัญชีของคุณจะถูกลบในอีก 90 วัน" |  | Show Message "บัญชีของคุณจะถูกลบในอีก 90 วัน" |  | Pass
De-02 | Delete Account | Delete Account With Wrong Password | Cannot Delete Account |  | Cannot Delete Account |  | Pass
Del-02 | Delete Account | Delete Account With Correct Password | Can Delete Account |  | Can Delete Account |  | Pass
Test Summary
No. of The Cases in Test Specification Document | [9 empty] | case(s)
Test Type | [7 empty] | UAT | API
Planned | [5 empty] | No. of Test Cases |  | 3 | 1 | case(s)
Actual | [7 empty] | 3 | 1 | case(s)
Passed | [7 empty] | 3 | 1 | case(s)
Failed | [7 empty] | 0 | 0 | case(s)
Total= | [7 empty] | 12 |  | case(s)
API Test Case
Test ID | Endpoint | Method | Module | Scenario | Expected Status | Actual Result | Response Time | Result
Del-01 | /api/users/me/request-delete | POSTMAN | Delete Account | Delete User Account | 200 OK | 200 OK | 606 ms | Pass
Defect Summary
No. of Defect Found: | [6 empty] | 0
Severity Levels
Low(1) | [6 empty] | 0
Medium(2) | [6 empty] | 0
High(3) | [6 empty] | 0
Critical(4) | [6 empty] | 0
Report Summary | [10 empty] | Meaning
Designing The Test: | 4 | [5 empty] | Person-hours |  |  |  | Security Level | Impact | Description
Test setup: | 5 | [5 empty] | Person-hours |  |  |  | 1 | Low | UI issues / cosmetic issues
Test Execution: | 3 | [5 empty] | Person-hours |  |  |  | 2 | Medium | Feature works incorrectly
Test Analysis and Report: | 6 | [5 empty] | Person-hours |  |  |  | 3 | High | Core function affected
Total Test Efforts: | 15 | [5 empty] | Person-hours |  |  |  | 4 | Critical | System crash
AverageTime Spend: | 7 | [5 empty] | Hours/defect
Meaning
[11 empty] | Priority Level | Impact | Description
[11 empty] | 1 | Low | Fix when time permits
[11 empty] | 2 | Medium | Should be fixed soon
[11 empty] | 3 | High | Must fix before release
[11 empty] | 4 | Critical | Immedoate fix required