## Sheet1
Test Summary Report
Test Report Date (dd-mm-yy) |  |  | 2026-04-03 |  | Version: | 1
Test Information
Project Name : | PaiNamNaeWebApp |  |  |  | Project ID: | Sprint 3
Start Date(dd-mm-yy): | 3/18/2026 |  |  |  | End Date: | 3/18/2026
Module Name : | Payment
Version : | v1.0 | [9 empty] | Chart Summary
Tester : | 1. จิตรานุช ประทุมวงศ์
Tester's Comments :
UAT Test Case
Test ID | Module | Test Scenario / Steps | Expected Result |  | Actual Result |  | Status
TC-PAY-001 | Login / Authentication | 1. เข้าสู่ระบบด้วยบัญชีผู้โดยสาร (Passenger) 2. กรอก Username และ Password 3. กดปุ่ม Login | ระบบพาผู้โดยสารเข้าสู่หน้าแรกและแสดงข้อมูลผู้ใช้ถูกต้อง |  | ระบบพาผู้โดยสารเข้าสู่หน้าแรกและแสดงข้อมูลผู้ใช้ถูกต้อง |  | PASS
TC-PAY-002 | Passenger Payment Flow | 1. นำทางไปยังหน้ารายการชำระเงิน 2. ตรวจสอบการแสดงผลรายการ | ระบบแสดงรายการชำระเงินทั้งหมดของผู้โดยสาร |  | ระบบแสดงรายการชำระเงินได้ครบถ้วน |  | PASS
TC-PAY-003 | Passenger Payment Flow | 1. กดปุ่ม "ชำระเงิน" ในรายการที่รอชำระ 2. ตรวจสอบหน้าต่าง (Modal) การชำระเงิน | ระบบแสดงหน้าต่างให้เลือกวิธีชำระเงิน (เงินสด, QR Code, โอนเงิน) |  | แสดงหน้าต่างให้เลือกวิธีชำระเงินครบทั้ง 3 วิธี |  | PASS
TC-PAY-004 | Cash Payment Flow | 1. เลือกวิธีชำระเงิน "เงินสด" 2. กดยืนยันการชำระเงิน | ระบบปรับสถานะรายการเป็น "รอยืนยันเงินสด" |  | ระบบปรับสถานะเป็น "รอยืนยันเงินสด" สำเร็จ |  | PASS
TC-PAY-005 | QR Code Payment Flow | 1. เลือกวิธีชำระเงิน "QR Code" 2. สแกนและอัปโหลดสลิป 3. กดยืนยัน | ระบบอัปโหลดสลิปและปรับสถานะเป็น "รอตรวจสอบ" |  | ระบบค้างอยู่ที่หน้าโหลดสลิปเป็นบางครั้งเมื่อใช้งานบนมือถือ |  | Fail
TC-PAY-006 | Bank Transfer Flow | 1. เลือกวิธีชำระเงิน "โอนธนาคาร" 2. อัปโหลดสลิป 3. กดยืนยัน | ระบบอัปโหลดสลิปและปรับสถานะเป็น "รอตรวจสอบ" |  | ระบบอัปโหลดสลิปและปรับสถานะได้อย่างถูกต้อง |  | PASS
TC-DRV-001 | Driver Verification Flow | 1. เข้าสู่ระบบบัญชีคนขับ 2. นำทางไปหน้ารายการที่รอดำเนินการ | ระบบแสดงรายการผู้โดยสารที่ชำระเงินเข้ามาและรอตรวจสอบ |  | ระบบแสดงรายการ pending payments ชัดเจน |  | PASS
TC-DRV-002 | Driver Verification Flow | 1. กดปุ่มอนุมัติ (Approve) บนการโอนเงิน 2. กรอกหมายเหตุ และกดยืนยัน | สถานะการชำระเงินเปลี่ยนเป็น "ชำระเรียบร้อย" |  | สถานะเปลี่ยนเป็น "ชำระเรียบร้อย" สลิปถูกต้อง |  | PASS
TC-DRV-003 | Driver Verification Flow | 1. กดปุ่มปฏิเสธ (Reject) บนสลิปที่ไม่ถูกต้อง 2. ระบุเหตุผล และกดยืนยัน | สถานะกลับเป็นรอชำระ และผู้โดยสารเห็นเหตุผลที่ปฏิเสธ |  | สถานะถูกปรับกลับเป็นให้ผู้โดยสารต้องชำระใหม่ แต่ผู้โดยสารไม่เห็นเหตุผลที่ถูกปฏิเสธ |  | Fail
TC-REC-001 | Receipt Document | 1. ผู้โดยสารกดปุ่มดู "ใบเสร็จรับเงิน" ในรายการที่ชำระเสร็จแล้ว | ระบบเปิดหน้าต่างเบราว์เซอร์ใหม่ แสดงใบเสร็จรับเงิน |  | ระบบเปิดใบเสร็จรับเงิน โดยมีข้อมูลครบถ้วน |  | PASS
TC-REC-002 | Tax Invoice Document | 1. ผู้โดยสารกดปุ่มดู "ใบกำกับภาษีอย่างย่อ" | ระบบเปิดหน้าต่างเบราว์เซอร์ใหม่ แสดงใบกำกับภาษี |  | ชื่อบริษัทในใบกำกับภาษีแสดงผลตัวอักษรภาษาไทยเพี้ยน (Encoding error) |  | Fail
Test Summary
No. of The Cases in Test Specification Document | [9 empty] | case(s)
Test Type | [7 empty] | UAT | API
Planned | [5 empty] | No. of Test Cases |  | 5 | 27 | case(s)
Actual | [7 empty] | 5 | 27 | case(s)
Passed | [7 empty] | 5 | 27 | case(s)
Failed | [7 empty] | 0 | 0 | case(s)
Total= | [7 empty] | 12 |  | case(s)
API Test Case
Test Id | Test Case Name | Module | Method | Endpoint | Auth Required | Test Type | Expected Status | Expected Result | Pass/Fail
1 | Create Payment - Success | Payment | POST | /api/payments | Bearer Token | Positive | 201 Created | Payment record created, status=pending | PASS
2 | Create Payment - No Token | Payment | POST | /api/payments | None | Negative | 401 Unauthorized | Error: Unauthorized | PASS
3 | Create Payment - Missing amount | Payment | POST | /api/payments | Bearer Token | Negative | 400 Bad Request | Error: amount is required | PASS
4 | Create Payment - Missing rideId | Payment | POST | /api/payments | Bearer Token | Negative | 400 Bad Request | Error: rideId is required | PASS
5 | Create Payment - Invalid rideId | Payment | POST | /api/payments | Bearer Token | Negative | 404 Not Found | Error: Ride not found | PASS
6 | Create Payment - Negative amount | Payment | POST | /api/payments | Bearer Token | Negative | 400 Bad Request | Error: amount must be positive | PASS
7 | Create Payment - Duplicate payment | Payment | POST | /api/payments | Bearer Token | Negative | 409 Conflict | Error: Payment already exists for this ride | PASS
8 | Upload Receipt - Success | Payment | POST | /api/payments/:paymentId/upload-receipt | Bearer Token | Positive | 200 OK | Receipt URL saved, status=uploaded | PASS
9 | Upload Receipt - No Token | Payment | POST | /api/payments/:paymentId/upload-receipt | None | Negative | 401 Unauthorized | Error: Unauthorized | PASS
10 | Upload Receipt - Invalid paymentId | Payment | POST | /api/payments/:paymentId/upload-receipt | Bearer Token | Negative | 404 Not Found | Error: Payment not found | PASS
11 | Upload Receipt - No file attached | Payment | POST | /api/payments/:paymentId/upload-receipt | Bearer Token | Negative | 400 Bad Request | Error: Receipt file is required | PASS
12 | Upload Receipt - Wrong file type | Payment | POST | /api/payments/:paymentId/upload-receipt | Bearer Token | Negative | 400 Bad Request | Error: Only image files are allowed | PASS
13 | Upload Receipt - Not payment owner | Payment | POST | /api/payments/:paymentId/upload-receipt | Other User Token | Negative | 403 Forbidden | Error: Forbidden (not owner) | PASS
14 | Verify Payment - Approve (Success) | Payment | PATCH | /api/payments/:paymentId/verify | Admin Token | Positive | 200 OK | status updated to verified/approved | PASS
15 | Verify Payment - Reject (Success) | Payment | PATCH | /api/payments/:paymentId/verify | Admin Token | Positive | 200 OK | status updated to rejected | PASS
16 | Verify Payment - No Token | Payment | PATCH | /api/payments/:paymentId/verify | None | Negative | 401 Unauthorized | Error: Unauthorized | PASS
17 | Verify Payment - User Token (not admin) | Payment | PATCH | /api/payments/:paymentId/verify | User Token | Negative | 403 Forbidden | Error: Forbidden (Admin only) | PASS
18 | Verify Payment - Invalid paymentId | Payment | PATCH | /api/payments/:paymentId/verify | Admin Token | Negative | 404 Not Found | Error: Payment not found | PASS
19 | Verify Payment - Missing status field | Payment | PATCH | /api/payments/:paymentId/verify | Admin Token | Negative | 400 Bad Request | Error: status is required | PASS
20 | Verify Payment - Invalid status value | Payment | PATCH | /api/payments/:paymentId/verify | Admin Token | Negative | 400 Bad Request | Error: status must be approved or rejected | PASS
21 | Verify Payment - Already verified | Payment | PATCH | /api/payments/:paymentId/verify | Admin Token | Negative | 409 Conflict | Error: Payment already verified | PASS
22 | Get Payment Detail - Success (Owner) | Payment | GET | /api/payments/:paymentId | Bearer Token | Positive | 200 OK | Full payment details returned | PASS
23 | Get Payment Detail - Success (Admin) | Payment | GET | /api/payments/:paymentId | Admin Token | Positive | 200 OK | Full payment details returned | PASS
24 | Get Payment Detail - No Token | Payment | GET | /api/payments/:paymentId | None | Negative | 401 Unauthorized | Error: Unauthorized | PASS
25 | Get Payment Detail - Invalid paymentId | Payment | GET | /api/payments/:paymentId | Bearer Token | Negative | 404 Not Found | Error: Payment not found | PASS
26 | Get Payment Detail - Not owner/admin | Payment | GET | /api/payments/:paymentId | Other User Token | Negative | 403 Forbidden | Error: Forbidden (not owner or admin) | PASS
27 | Get Payment Detail - Invalid Token | Payment | GET | /api/payments/:paymentId | Invalid Token | Negative | 401 Unauthorized | Error: Invalid or expired token | PASS
Report Summary | [10 empty] | Meaning
Designing The Test: | 5 | [5 empty] | Person-hours |  |  |  | Security Level | Impact | Description
Test setup: | 10 | [5 empty] | Person-hours |  |  |  | 1 | Low | UI issues / cosmetic issues
Test Execution: | 15 | [5 empty] | Person-hours |  |  |  | 2 | Medium | Feature works incorrectly
Test Analysis and Report: | 6 | [5 empty] | Person-hours |  |  |  | 3 | High | Core function affected
Total Test Efforts: | 15 | [5 empty] | Person-hours |  |  |  | 4 | Critical | System crash
AverageTime Spend: | 10 | [5 empty] | Hours/defect
Meaning
[11 empty] | Priority Level | Impact | Description
[11 empty] | 1 | Low | Fix when time permits
[11 empty] | 2 | Medium | Should be fixed soon
[11 empty] | 3 | High | Must fix before release
[11 empty] | 4 | Critical | Immedoate fix required